## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Initialize project repository and configure base environment settings | Set up monorepo directory structure for backend (Express + Bun) and frontend (Vite + React 19). Configure TypeScript tsconfig, Prettier/ESLint formatting rules, environment variable templates (.env.example), and core repository documentation. | 1 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/1 | Closed | ldanh270 | 19/05/2026 | 31/05/2026 | Sprint 1 | Task, 3_Done | System & Core
Configure Express server infrastructure and database connection module | Initialize Express 5 server infrastructure with CORS middleware, standard JSON body parsers, centralized AppError class handling, database connector module in backend/src/lib/database.ts, and bootstrap script in backend/src/app.ts. | 2 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/2 | Closed | ldanh270 | 26/05/2026 | 31/05/2026 | Sprint 1 | Feature, 3_Done | System & Core
Configure development workflow automation scripts and agent directives | Add architecture constitution in AGENTS.md and project context in GEMINI.md. Set up multi-agent role directives, SOLID compliance checklists, design pattern guidelines, and helper execution scripts for development automation. | 3 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/3 | Closed | ldanh270 | 26/05/2026 | 31/05/2026 | Sprint 1 | Task, 3_Done | System & Core
Set up React 19 frontend architecture and routing system | Initialize Vite + React 19 + TypeScript frontend application. Configure Tailwind CSS semantic design tokens, HSL color palette variables, global layout shell, router navigator singleton (@/lib/router-navigator), and base page route definitions. | 4 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/4 | Closed | ldanh270 | 28/05/2026 | 31/05/2026 | Sprint 1 | Task, 3_Done | System & Core
Implement employee profile viewing, editing, and avatar upload | Build employee profile details view and edit modal forms. Integrate Cloudinary media service for uploading and updating profile avatar images. Implement client-side form validation, state management, and toast notifications. | 5 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/5 | Closed | ldanh270 | 28/05/2026 | 31/05/2026 | Sprint 1 | Feature, 3_Done | Employee Management
Implement user authentication login and logout flows | Develop JWT-based authentication service (AuthService.login, AuthService.logout). Create backend authentication routes, password hashing utilities using bcrypt, and React login/logout UI components integrated with React Query. | 6 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/6 | Closed | bloan-7105 | 31/05/2026 | 31/05/2026 | Sprint 1 | Feature, 3_Done | Auth & Security
Configure database seeders and register initial demo data | Build seed scripts for populating default system roles, administrative users, sample departments, and test employees. Add seeder execution runner with skip check verification for clean database environment initialization. | 7 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/7 | Closed | ldanh270 | 19/05/2026 | 31/05/2026 | Sprint 1 | Task, 3_Done | System & Core
Implement JWT authorization middleware and password reset flow | Build requireAuth middleware for protecting private routes via JWT verification. Implement forgot password and reset password API endpoints, email notification helper, and frontend password reset form components. | 8 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/8 | Closed | ldanh270 | 01/06/2026 | 08/06/2026 | Sprint 2 | Feature, 3_Done | Auth & Security
Refactor frontend navigation menu and modular subsystem routing | Restructure React Router configuration into modular subsystem URLs with legacy redirects. Implement client-side route guards, navigation breadcrumbs, and responsive sidebar navigation layout. | 9 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/9 | Closed | ldanh270 | 01/06/2026 | 08/06/2026 | Sprint 2 | Task, 3_Done | System & Core
Design Prisma database schema and execute initial SQL migrations | Define core domain entities in prisma/schema.prisma including Employee, User, Role, Department, and RefreshToken models. Execute initial Prisma migrations to generate PostgreSQL database tables and foreign key constraints. | 10 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/10 | Closed | ldanh270 | 01/06/2026 | 08/06/2026 | Sprint 2 | Feature, 3_Done | System & Core
Refine database migration workflow and employee data seeder | Add employee contract and insurance configuration seeders (employee-contract.config.ts). Enhance migration execution scripts and ensure fail-safe database seeding during development environment setup. | 11 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/11 | Closed | ldanh270 | 01/06/2026 | 08/06/2026 | Sprint 2 | Task, 3_Done | System & Core
Implement backend CRUD APIs for salary components | Build backend service and controller for managing salary components (base salary, allowances, bonuses, deductions). Define Zod input validation schemas, DTOs, and repository queries for salary component management. | 12 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/12 | Closed | bloan-7105 | 01/06/2026 | 08/06/2026 | Sprint 2 | Feature, 3_Done | Payroll System
Implement project creation and project member assignment | Build ProjectService and APIs for creating projects, editing project metadata, adding members to projects, and removing members. Define project member roles and database relations in Prisma schema. | 13 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/13 | Closed | ldanh270 | 01/06/2026 | 08/06/2026 | Sprint 2 | Feature, 3_Done | Project Management
Develop automated payroll calculation service and approval workflow | Implement payroll calculation engine combining worked hours, overtime rates, and salary component rules. Build payroll approval workflow (submitPayroll, approvePayroll, rejectPayroll) with transaction safety. | 14 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/14 | Closed | ldanh270 | 01/06/2026 | 08/06/2026 | Sprint 2 | Feature, 3_Done | Payroll System
Implement personal payslip viewing and monthly payment history | Build employee self-service endpoint GET /api/payroll/me/payslips and React UI page for viewing detailed monthly payslips, earnings breakdowns, tax deductions, and PDF export functionality. | 15 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/15 | Closed | ldanh270 | 09/06/2026 | 11/06/2026 | Sprint 3 | Feature, 3_Done | Payroll System
Build custom salary formula setup and MathJS formula validator | Integrate MathJS library for parsing dynamic salary calculation formulas. Build backend endpoint POST /api/payroll/formulas/validate to verify formula syntax and variable dependencies before saving. | 16 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/16 | Closed | ldanh270 | 09/06/2026 | 11/06/2026 | Sprint 3 | Feature, 3_Done | Payroll System
Implement automated email notifications for published payslips | Build email delivery service using Nodemailer to send payslip notification emails to employees upon payroll approval. Add tracking for employee payslip view confirmation and delivery audit status. | 17 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/17 | Closed | bloan-7105 | 09/06/2026 | 11/06/2026 | Sprint 3 | Feature, 3_Done | Payroll System
Implement payroll generation settings and period lock workflow | Build administration settings for automatic monthly payroll generation schedules. Add period locking logic to prevent edits to payroll entries once approved and archived for financial compliance. | 18 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/18 | Closed | ldanh270 | 09/06/2026 | 11/06/2026 | Sprint 3 | Feature, 3_Done | Payroll System
Enhance employee directory with status tabs and profile editing | Refactor employee list view with status filter tabs (Active, Locked, Terminated). Synchronize URL query parameters with search filters and restore employee profile editing dialog components. | 19 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/19 | Closed | bloan-7105 | 09/06/2026 | 11/06/2026 | Sprint 3 | Defect, 3_Done | Employee Management
Build advanced employee search, filtering, and pagination | Implement server-side search and filtering for employee directory by name, department, role, and employment status. Connect URL search params to React Query hook for bookmarkable search state. | 20 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/20 | Closed | ldanh270 | 09/06/2026 | 11/06/2026 | Sprint 3 | Feature, 3_Done | Employee Management
Implement working shift CRUD APIs and shift registration | Build ShiftService and routes for managing shift templates (Morning, Afternoon, Night, Flexible). Implement endpoints for employees to view assigned working shifts and submit shift preference requests. | 21 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/21 | Closed | Xuan Thang | 09/06/2026 | 11/06/2026 | Sprint 3 | Feature, 3_Done | Attendance & Shift
Design Application subsystem database schema and core APIs | Define Prisma models for leave requests, business trip proposals, and regime applications. Build backend API endpoints for creating, retrieving, and updating application status with Zod input validation. | 22 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/22 | Closed | Nguyen Anh Tuyet | 12/06/2026 | 13/06/2026 | Sprint 4 | Feature, 3_Done | Application Subsystem
Build multi-step employee creation wizard UI and validation | Implement React multi-step wizard component (EmployeeCreateWizard.tsx) covering personal info, job details, contract terms, and user credentials. Add Zod schema validation per wizard step. | 23 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/23 | Closed | ldanh270 | 12/06/2026 | 13/06/2026 | Sprint 4 | Defect, 3_Done | Employee Management
Implement JWT refresh token rotation and session persistence | Build refresh token endpoint POST /api/auth/refresh with token rotation and cookie storage. Add Axios interceptor in frontend to handle automatic token refresh on 401 Unauthorized responses seamlessly. | 24 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/24 | Closed | ldanh270 | 12/06/2026 | 13/06/2026 | Sprint 4 | Defect, 3_Done | Auth & Security
Implement task management CRUD APIs and assignee selection | Build TaskService and controllers for creating tasks, assigning team members, updating task status (To Do, In Progress, Review, Done), setting task priorities, and tracking task completion deadlines. | 25 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/25 | Closed | Doannhat219 | 12/06/2026 | 13/06/2026 | Sprint 4 | Feature, 3_Done | Task Management
Build dynamic application creation UI and leave request forms | Build frontend feature components for submitting leave applications, overtime requests, and work proposals. Add dynamic form inputs based on selected application type and attachments file upload. | 26 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/26 | Closed | Nguyen Anh Tuyet | 13/06/2026 | 13/06/2026 | Sprint 4 | Feature, 3_Done | Application Subsystem
Build attendance timesheet dashboard and virtual QR scanner UI | Implement React timesheet dashboard displaying daily check-in/out records. Create virtual scanner component (VirtualScanner.tsx) for simulating QR code check-in and GPS check-in during testing. | 27 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/27 | Closed | Xuan Thang | 13/06/2026 | 13/06/2026 | Sprint 4 | Feature, 3_Done | Attendance & Shift
Integrate GPS geofencing and location-based attendance check-in | Implement Geolocation API integration in check-in service. Add geofence radius check against office GPS coordinates to prevent proxy check-in and ensure location compliance. | 28 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/28 | Closed | Xuan Thang | 13/06/2026 | 13/06/2026 | Sprint 4 | Feature, 3_Done | Attendance & Shift
Build permission-based authorization middleware (requirePermission) | Implement backend middleware requirePermission(permissionName) that evaluates user permissions dynamically from database roles instead of hardcoded single-role string checks. | 29 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/29 | Closed | ldanh270 | 13/06/2026 | 15/06/2026 | Sprint 5 | Defect, 3_Done | Auth & Security
Build user security settings UI and password change modal | Create frontend security tab in profile page allowing users to update their password, view active sessions, and review recent login timestamps with toast feedback. | 30 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/30 | Closed | bloan-7105 | 14/06/2026 | 15/06/2026 | Sprint 5 | Feature, 3_Done | Auth & Security
Implement login activity logging and suspicious activity detection | Build backend audit logging service (AuditService.logActivity) to capture IP addresses, user agents, and timestamps on authentication events. Add rule engine to flag suspicious login attempts. | 31 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/31 | Closed | bloan-7105 | 14/06/2026 | 15/06/2026 | Sprint 5 | Feature, 3_Done | Auth & Security
Implement project dashboard UI and project details view | Create React pages for project management including project cards overview, progress indicators, project member lists, member position management, and project settings drawer. | 32 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/32 | Closed | Doannhat219 | 14/06/2026 | 15/06/2026 | Sprint 5 | Feature, 3_Done | Project Management
Build employee shift registration page and clock-in/out UI | Develop frontend clock-in/out interface with live digital clock, current shift status indicator, GPS location confirmation prompt, and shift registration request modal. | 33 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/33 | Closed | Xuan Thang | 14/06/2026 | 15/06/2026 | Sprint 5 | Feature, 3_Done | Attendance & Shift
Implement payroll formula syntax parser and dependency resolver | Enhance formula validation logic to check for circular variable references, undefined component variables, and division-by-zero errors in custom compensation formulas. | 34 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/34 | Closed | ldanh270 | 14/06/2026 | 15/06/2026 | Sprint 5 | Defect, 3_Done | Payroll System
Build security threat detection alerts and automated account lockout | Implement security guard that automatically locks user accounts after consecutive failed login attempts. Generate security alert records for administrator audit review. | 35 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/35 | Closed | bloan-7105 | 14/06/2026 | 15/06/2026 | Sprint 5 | Defect, 3_Done | Auth & Security
Add interactive GPS map picker and office radius config UI | Integrate map location picker component for administrators to set office GPS coordinates and maximum allowed check-in distance radius (geofence perimeter). | 36 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/36 | Closed | Xuan Thang | 16/06/2026 | 21/06/2026 | Sprint 6 | Feature, 3_Done | Attendance & Shift
Build user account settings page and security preferences UI | Create comprehensive account management page supporting profile photo removal, personal details update, security alert subscription settings, and session termination actions. | 37 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/37 | Closed | bloan-7105 | 16/06/2026 | 21/06/2026 | Sprint 6 | Feature, 3_Done | Auth & Security
Implement interactive Kanban board for task status management | Build React Kanban board component with column status lanes (To Do, In Progress, Code Review, Completed). Enable task card drag-and-drop or status dropdown transitions. | 38 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/38 | Closed | Doannhat219 | 16/06/2026 | 21/06/2026 | Sprint 6 | Feature, 3_Done | Task Management
Implement weekly schedule templates and auto-scheduler runner | Build WeeklyScheduleTemplateService for configuring recurring weekly shift patterns. Add scheduler function to auto-generate weekly employee work schedules ahead of time. | 39 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/39 | Closed | Xuan Thang | 17/06/2026 | 21/06/2026 | Sprint 6 | Feature, 3_Done | Attendance & Shift
Implement annual leave balance calculation engine and carry-over rules | Build business logic for tracking paid leave entitlements, accruals per month, leave deductions upon request approval, and automatic annual carry-over rules. | 40 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/40 | Closed | Nguyen Anh Tuyet | 19/06/2026 | 21/06/2026 | Sprint 6 | Feature, 3_Done | Application Subsystem
Build interactive project Gantt chart UI with saved filter presets | Implement Gantt chart component for visual project timeline tracking. Add support for saving custom query filter presets (by assignee, status, milestone, category) to localStorage. | 41 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/41 | Closed | Doannhat219 | 21/06/2026 | 21/06/2026 | Sprint 6 | Feature, 3_Done | Task Management
Implement security audit dashboard UI and login activity logs table | Build administrator dashboard for security monitoring, displaying recent login activity logs, failed login attempt charts, active user sessions, and security alerts table. | 42 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/42 | Closed | bloan-7105 | 21/06/2026 | 21/06/2026 | Sprint 6 | Defect, 3_Done | Auth & Security
Implement formatted attendance report Excel export service | Build backend export service generating styled Excel workbooks (.xlsx) for monthly employee attendance summaries, late arrivals, early departures, and total worked hours. | 43 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/43 | Closed | Xuan Thang | 25/06/2026 | 02/07/2026 | Sprint 7 | Feature, 3_Done | Attendance & Shift
Implement spent time log UI and Redmine-compatible layout | Build SpentTimeService and frontend components for logging work hours spent on tasks. Align table pagination, navigation sidebars, and filters with Redmine UX standards. | 44 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/44 | Closed | Doannhat219 | 27/06/2026 | 02/07/2026 | Sprint 7 | Feature, 3_Done | Project Management
Add background cron job for automatic weekly schedule generation | Configure background task scheduler using node-cron to generate employee work schedules every week based on active WeeklyScheduleSettings and holiday calendars. | 45 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/45 | Closed | Xuan Thang | 28/06/2026 | 02/07/2026 | Sprint 7 | Feature, 3_Done | Attendance & Shift
Implement dynamic RBAC architecture with custom role permissions | Build complete RBAC engine allowing super-admins to define custom roles, map modular permissions (create, read, update, delete per feature), and dynamically evaluate access rights. | 46 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/46 | Closed | bloan-7105 | 25/06/2026 | 02/07/2026 | Sprint 7 | Feature, 3_Done | Auth & Security
Build interactive permission matrix UI and role assignment table | Create React permission matrix component (PermissionMatrix.tsx) for managing role-permission mappings with checkboxes. Add support for direct permission overrides per employee. | 47 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/47 | Closed | bloan-7105 | 25/06/2026 | 02/07/2026 | Sprint 7 | Feature, 3_Done | Auth & Security
Build system roles CRUD APIs and role-permission mapping endpoints | Implement backend endpoints GET /api/roles, POST /api/roles, POST /api/roles/:id/permissions for full lifecycle management of application roles and security permissions. | 48 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/48 | Closed | bloan-7105 | 25/06/2026 | 02/07/2026 | Sprint 7 | Feature, 3_Done | Auth & Security
Harden payroll generation with Prisma database transactions | Wrap generatePayroll and payroll approval operations inside Prisma interactive transactions () to guarantee atomic all-or-nothing execution and prevent race conditions. | 49 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/49 | Closed | ldanh270 | 25/06/2026 | 02/07/2026 | Sprint 7 | Defect, 3_Done | Payroll System
Implement part-time availability submission API and UI drawer | Build PartTimeAvailabilityService enabling part-time employees to declare weekly available time slots. Create administrator UI drawer for viewing availability and assigning shifts. | 50 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/50 | Closed | Xuan Thang | 07/07/2026 | 14/07/2026 | Sprint 8 | Feature, 3_Done | Attendance & Shift
Build task category management UI and custom query URL sync | Implement UI pages for managing task categories (Bug, Feature, Support, Documentation). Connect custom task query state to URL parameters for shareable task views. | 51 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/51 | Closed | Doannhat219 | 07/07/2026 | 14/07/2026 | Sprint 8 | Feature, 3_Done | Task Management
Implement usePermission hook and permission-guarded UI components | Build custom React hook usePermission and wrapper component <PermissionGuard permission='...'> to conditionally render action buttons and page sections based on user permissions. | 52 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/52 | Closed | bloan-7105 | 07/07/2026 | 14/07/2026 | Sprint 8 | Defect, 3_Done | Auth & Security
Refactor React Router route protection with permission checks | Upgrade router route definitions to wrap protected routes with permission authorization checks. Redirect unauthorized users to access denied page without crashing React state. | 53 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/53 | Closed | bloan-7105 | 07/07/2026 | 14/07/2026 | Sprint 8 | Defect, 3_Done | Auth & Security
Add comprehensive unit tests for PayrollService and formula engines | Write Vitest/Jest unit test suites covering PayrollService, formula evaluation, status transitions, tax calculations, and edge cases with mocked repositories. | 54 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/54 | Closed | bloan-7105 | 13/07/2026 | 14/07/2026 | Sprint 8 | Testing, 3_Done | Payroll System
Add unit test suite for AuthService, RoleService & CacheService | Write unit tests for authentication logic, password hashing, JWT token verification, in-memory cache eviction, and permission checks with high code coverage. | 55 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/55 | Closed | bloan-7105 | 14/07/2026 | 14/07/2026 | Sprint 8 | Testing, 3_Done | Auth & Security
Add unit test suite for TaskService and ProjectService | Write backend unit test suites verifying project CRUD operations, task creation validation, member assignment restrictions, and spent time log calculations. | 56 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/56 | Closed | Doannhat219 | 14/07/2026 | 18/07/2026 | Sprint 9 | Testing, 3_Done | Task Management
Add unit test suite for AttendanceService and ShiftService | Write unit tests for check-in/out time calculations, late arrival detection, geofence coordinate validation, and shift schedule assignment rules. | 57 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/57 | Closed | Xuan Thang | 14/07/2026 | 18/07/2026 | Sprint 9 | Testing, 3_Done | Attendance & Shift
Implement multi-level application approval engine and regime requests | Build backend service for hierarchical application approvals (Manager -> HR -> Admin). Support specialized application types for maternity regime, recruitment proposal, and travel. | 58 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/58 | Closed | Nguyen Anh Tuyet | 14/07/2026 | 18/07/2026 | Sprint 9 | Feature, 3_Done | Application Subsystem
Add end-to-end integration tests for application submission and approval | Implement integration tests for full application lifecycle: creation by employee, notification dispatch, manager approval/rejection, and leave balance update verification. | 59 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/59 | Closed | Nguyen Anh Tuyet | 16/07/2026 | 18/07/2026 | Sprint 9 | Testing, 3_Done | Application Subsystem
Add unit tests for PtShiftSuggestionService and assignment algorithms | Build comprehensive unit test suite validating part-time shift suggestion algorithm, availability score calculations, shift conflict checks, and fallback mechanisms. | 60 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/60 | Closed | Xuan Thang | 15/07/2026 | 18/07/2026 | Sprint 9 | Testing, 3_Done | Attendance & Shift
Implement weekly/monthly workforce timesheet and employee search sync | Build interactive workforce timesheet grid component displaying schedule status per employee per day. Add real-time search filtering and work shift assignment drawer. | 61 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/61 | Closed | Xuan Thang | 18/07/2026 | 18/07/2026 | Sprint 9 | Feature, 3_Done | Attendance & Shift
Implement shift change request workflow and approval sheet UI | Build APIs and frontend bottom-sheet component allowing employees to request shift swaps with colleagues. Add manager approval workflow for confirming shift change requests. | 62 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/62 | Closed | Nguyen Anh Tuyet | 18/07/2026 | 24/07/2026 | Sprint 10 | Feature, 3_Done | Application Subsystem
Implement Workforce Capacity Copilot forecasting board and cron job | Build AI-assisted weekly capacity forecast board (CapacityCopilotBoard.tsx). Add permission gate project:capacity:forecast and automated weekly forecast background task. | 63 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/63 | Closed | Xuan Thang | 19/07/2026 | 24/07/2026 | Sprint 10 | Feature, 3_Done | Workforce Capacity Copilot
Implement AI task assignee suggester and project task decomposition UI | Build TaskEstimateAiService integrating Gemini API. Create frontend dialogs for AI-recommended task assignee based on skill/workload, and AI automated project task generator modal. | 64 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/64 | Closed | Doannhat219 | 19/07/2026 | 24/07/2026 | Sprint 10 | Testing, 3_Done | Task Management
Implement automated part-time shift suggestion engine and E2E tests | Build PtShiftSuggestionService that matches part-time employee availability with unassigned work shifts. Add navigation routing fixes and Playwright E2E verification tests. | 65 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/65 | Closed | Xuan Thang | 23/07/2026 | 24/07/2026 | Sprint 10 | Feature, 3_Done | Attendance & Shift
Implement complete Recruitment subsystem APIs, UI pages, and connectors | Build comprehensive recruitment module including Job Requisitions, Candidate Intake, Kanban Candidate Pipeline, Job Postings, Background Checks, Interview Scheduling, Offer Letters, and OAuth job board connectors. | 66 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/66 | Closed | ldanh270 | 20/07/2026 | 24/07/2026 | Sprint 10 | Feature, 3_Done | Recruitment Subsystem
Implement Employee Contracts management, renewals, and Insurance module | Build backend services and React pages for Employee Contracts CRUD (/employees/contracts), digital contract signing workflow, contract renewal/termination alerts, and Social Insurance profiles CRUD. | 67 | https://github.com/ldanh270/integrated-hr-and-product-system/issues/67 | Open | ldanh270 | 24/07/2026 | 24/07/2026 | Sprint 10 | Feature, 1_To Do | Contracts & Insurance